## Sprint Plan
Week | Date | Goal | Expected Deliverable | Milestone
3 | 09/04/2026 | README + Skeleton + Sprint Plan | All M1 files ready | M1
4 | 16/04/2026 | EDA + Data Cleaning | Clean dataset + initial plots
5 | 23/04/2026 | Build ML baseline | Logistic Regression + KNN working | M2
6 | 30/04/2026 | Feature Engineering + App Structure | Improved features + Streamlit structure
7 | 07/05/2026 | Model Evaluation | Accuracy + confusion matrix
8 | 14/05/2026 | Dashboard + Final Model | Working Streamlit app | M3
9 | 28/05/2026 | Improvements + UI polish | Final improved version
10 | 11/06/2026 | Demo Day | Presentation ready | Final